レジリアンスプロジェクト
事務局会議議事録（案）


２００７年６月２５日（月）１３：３０－１４：３０

出席者：梅津、佐伯、Thamana、宮嵜、入江

Minutes of Project Meeting 25 June, 2007, 13:30-

Attended by: Umetsu, Saeki, Thamana, Miyazaki, Irie

議題：Agenda

0． １８回レジリアンスセミナーの反省

討議記録を取るべきか？( 要旨の掲載から始める

    Feedback from 18th Resilience Seminar: Need to record main discussions?

1． 雨量計の設置訓練７月１１－１２、１８－１９日（担当：佐伯）

( 雨量計がいつ届くかを確認してから日程を調整する

Rain gauge installation training at RIHN (July 11-12, 18-19)　 Coordination: Saeki

( Saeki san need to check when the rain gauge arrives at RIHN.

2． ルサカワークショップ日程案９月３日（月）（担当：タマナ）

( 会場の予約、プログラム、参加者のリストアップを進める

Lusaka WS September, 3: (Coordination: Thamana)

(　Thamana san will start reservation of the conference room at Juls guesthouse, making list of participants, and WS program.

3． 日本からの荷物の発送及びルサカでの空港受け取り（担当：吉村、佐伯）

( 吉村さんに締め切りを設定してもらう。

Shipping equipment from Japan and receiving at Lusaka Airport (Coordination: Yoshimura)

　　( Yoshimura san will call deadline of the list of equipments to be shipped to Lusaka.

4． その他の連絡

―１８年度業績提出締め切り（７月４日まで入江さんへ）( 梅津、タマナのみ

-FY2006 Publication and Research Activities due July 4th (submit to Irie san) (only Umetsu & Thamana

―１９回レジリアンスセミナーについて

講師：吉田憲司（民博）７月３０日（月）講演室を予定（担当：宮嵜）( 要旨をもらう。また次回１０月の第２１回レジリアンスセミナーの講師候補を考える。

- 19th Resilience Seminar: Speaker Dr. Kenji Yoshida, Museum of Ethnology, July 30th, 15:30-　(　abstract required. We need to consider the candidate of speaker for the next Resilience Seminar in October.

―夏休みの予定を各自決めてボードへ

-summer-holiday schedule (please write up on the board)

―Dr. Lawrence Flint （平成２０年２月４日―５月３日）7/8 PL会議で承認

-Dr. Lawrence Flint has changed the start of his fellowship to Feb 4-May 3, 2008.

次回の会議：７月９日（月）15:00- 

Next Meeting: 9th July 15:00- 

�PAGE \# "'ページ : '#'�'"  ��





